## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | REACT COMPONENTS
1.1 | admin profile | 2 | Abuelleil | harb | lamei
1.2 | login page/main page | 2 | Harb | lamei | yasmeen
1.3 | registration page | 2 | yasmeen | lamei | joe
1.4 | user profile | 2 | lamei | mehaya | abdallah
1.5 | consultancy profile | 2 | alie | nour | hazem
1.6 | partner profile | 2 | mehaya | hazem | alie
1.7 | display task info | 2 | hazem | nour | mehaya
1.8 | display certification | 2 | abdallah | joe | joe
1.9 | admin certification review page | 2 | joe | harb | abdallah
2 | admin view uploaded tasks | 2 | nour | joe | hazem
2.1 | admin sees notifications | 2 | Abuelleil,Harb | yasmeen | nour
2.2 | partner can create a new task | 2 | yasmeen,lamei | abuelleil | nour
2 | user can apply for certification | 2 | alie,mehaya | yasmeen | yasmeen
2.3 | user sees notifications | 2 | hazem,nour | abuelleil | lamei
2.4 | partner sees notifications | 2 | abdallah, joe | harb | harb
2.5
2.6
2.7
2.8
2.9
3
3.1
3.2
3.3
3.4
3.5
3.6
3.7
3.8
3.9
4
4.1
4.2
4.3
4.4
4.5
4.6
4.7
4.8
4.9
5
5.1
5.2
5.3
5.4
5.5
5.6
5.7
5.8
5.9
6