## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | CRUD TESTING:
1.1 | Admin Crud tests | 2 | Abuelleil | harb | hazem
1.2 | Partner Crud Test | 2 | Alie | youssef | abuelleil
1.3 | User Crud Test | 2 | Mehaya | yasmeen | abdallah
1.4 | Certificate Crud Test | 2 | Harb | lamei | yasmeen
1.5 | Notification Crud Test | 2 | Youssef | abdallah | mehaya
1.6 | Task Crud Test | 2 | Yasmeen,Lamei | abdallah | youssef
1.7 | Consultancy Crud Test | 2 | Abdallah | lamei | youssef
1.8 | Application Crud Test | 2 | Hazem | abuelleil | yasmeen
1.9
2 | Consultancy User Stories : (Main module)
2.1 | Consultancy negotiates with admin & Unit Test | 2 | Harb | lamei | abdallah
2.2 | Consultancy can apply for Task Unit Test | 2 | Abuelleil | lamei | youssef
2 | Contact Admin (through email) | 2 | Mehaya | abdallah | alie
2.3 | User User Stories: (Main Module)
2.4 | Browse Vacancies that match the user's certifications | 5 | Abuelleill | mehaya | yasmeen
2.5 | User can Apply for a Task | 2 | hazem | abuelleil | youssef
2.6 | get a notification upon being accepted or rejected | 3 | alie | mehaya | alie
2.7
2.8 | Admin User Stories: (Main Module)
2.9 | view a task's description | 2 | hazem | lamei | yasmeen
3 | get notified when a consultancy applies for a task | 2 | hazem | abuelleil | harb
3.1 | gets notified when a partner submits a task description | 2 | abuelleil | hazem | harb
3.2 | gets notified when a user applies for a task | 3 | mehaya | alie | hazem
3.3 | view users profile and perform interviews (receive contact info) | 2 | yasmeen | abdallah | youssef
3.4 | be in contact with partner (send and recieve contact info) | 2 | mehaya | yasmeen | abuelleil
3.5 | upload tasks after negotiation step is over (with consultancy and partner) | 2 | lamei | hazem | abuelleil
3.6 | Set attributes of task | 2 | lamei | yasmeen | youssef
3.7 | assign users to a task | 2 | nour | harb | hazem
3.8 | assign consultancy to a task | 2 | nour | harb | abdallah
3.9
4 | Partner User Stories: (Main Module)
4.1 | Partner can view his/her profile | 2 | abdallah | alie | mehaya
4.2 | submit task description to be posted | 2 | joe | alie | lamei
4.3 | be in contact with Admin to discuss task description (send and receive contact info) | 2 | alie | hazem | harb
4.4
4.5 | User User Stories: (Sub Module)
4.6 | Search for certification | 2 | harb | lamei | hazem
4.7 | get certificate recommendations to improve user certifications | 5 | yasmeen | youssef | mehaya
4.8 | apply for certification | 2 | abuelleil | abdallah | mehaya
4.9 | undergo evaluation process(whether online or offline) | 2 | harb | youssef | abuelleil
5 | get notified with the details of evaluation process
5.1
5.2 | Admin User Stories: (Sub Module)
5.3 | approve user certifications & Test | 2 | mehaya | alie | abdallah
5.4 | get notified when a user applies for certifications & Test | 3 | lamei | mehaya | alie
5.5
5.6
5.7
5.8
5.9
6